## BLANK Product Backlog
CHIRP BACKLOG
PRODUCT BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
| Client | See the main pages of my app ( Login, Feed, Users, Settings) | I can navigate trough the app | Medium | 1 | Complete | Not Started | High
| App | Have a database where store my users and posts | I dont loose any information | High | 2 | Complete | In Progress | Medium
| Client | Be able to create an account | I can post chirps | Medium | 2 | Complete | Complete | Low
| Client | Send chirps | Others see my chirps | Medium |  | Complete | Overdue
| Client | Send chirps with @mentions | Others get notified | Low | 3 | Not Started | On Hold
| Client | Send chirps with images |  | Low |  | Not Started
| Admin | Be able to remove users | I can moderate the feed | Low |  | Not Started
| Client | Be able to see the most liked chirps |  | Low |  | Not Started
| App | Have a cloud hosting with a database |  | High | 4 | In Progress
|  |  |  | Low | 0 | Not Started
|  |  |  | Low | 0 | Not Started
|  |  |  | Low | 0 | Not Started
|  |  |  | Low | 0 | Not Started
|  |  |  | Low | 0 | Not Started
TOTAL |  |  |  |  | 12